## 2020.01.22 Rev Phase-wise Est.
Proposed Khushboo Campus at Tauru, Haryana
| Budgetary Estimate | [8 empty] | Phase-wise Allocation of Budget
Modules | Item |  | Description | Area to be Developed | Covered Area | Buit up Area in Sqm | Rate Rs./ sqm | Amount in Rs. | Status | Phase -0 | Phase -1a | Ph-1b | Ph-2 | Ph-3
M-0 | Land,Govt approval,Electricity,Water and Boundary wall |  |  | In Sqm | In Sqm |  | per sqm | in INR (Rs.) | Completed | Land,Govt approval,Electricity,Water and Boundary wall | In INR | In INR | In INR | In INR
|  | a | Land | 12140 |  |  |  | 22000000
|  | b | Boundary Wall |  |  |  |  | 7500000
|  | c | Electricity and Water |  |  |  |  | 500000
|  |  | S.Total |  |  |  |  | 30000000
M - 1 | Infrastructure Site Development, Landscape Roads, Parking, Plumbing + Electricals Infra, Ancillary bldgs. & STP | a | Site Development | 11567 |  | 0 | 450 | 5205150 | Completed |  | 1821802.5 | 780772.5 | 1301287.5 | 1301287.5
|  | b | Road Infrastructure (roads and parking areas) | 2400 |  |  | 2000 | 4800000 |  |  | 2400000 | 960000 | 720000 | 720000
|  | c | Landscape & Planting (swails, ponds, trees shrubbery, orchard & farms) | 5000 |  |  | 720 | 3600000 |  |  | 1800000 | 360000 | 540000 | 900000
|  | d | Irrigation | 5000 |  |  | 180 | 900000 |  |  | 450000 | 90000 | 135000 | 225000
|  | e | Guard House, Gates & ancillary buildings |  | 60 |  | 12000 | 720000 | Completed |  | 720000
|  | f | Paths & Paving | 1500 |  |  | 2500 | 3750000 |  |  | 1125000 | 562500 | 562500 | 1500000
|  | g | Electrical Infra (Excl. DG) |  |  |  |  | 3000000 |  |  | 900000 | 450000 | 450000 | 1200000
|  | h | Outdoor Lighting |  |  |  |  | 600000 |  |  | 210000 | 90000 | 90000 | 210000
|  | i | Plumbing Infra |  |  |  |  | 3000000 |  |  | 900000 | 450000 | 450000 | 1200000
|  | j | STP (decentralized & DEWATS) |  |  |  |  | 1500000 |  |  | 150000 | 150000 | 225000 | 975000
|  | k | Staff Qtrs. (2 nos) on GF |  | 70 |  | 18000 | 1250000 |  |  |  |  | 1250000
M - 2 | Main Building - Ground Floor |  | School, Therapy & Offices |  | 1360 | 1565 | 20500 | 27880000 | [5 empty] | 27880000
| Solar PV - 50Kw (60,000 / Kw) | [6 empty] | 3000000 |  |  | 600000 | 300000 | 900000 | 1200000
Family Homes (FH)
M - 3 | FH - 4, Ground + 1st Floor |  | Family Home |  | 241 | 321 | 18500 | 4458500 |  |  |  |  | 4458500
M - 4 | FH - 2 & 3 - Ground Floor only |  | Family Homes |  | 264 | 350 | 19000 | 5016000 |  |  |  |  | 5016000
M - 5 | FH - 2 & 3 - 1st Floor |  | Family Homes |  | 251 | 284 | 18000 | 4518000 |  |  |  |  | 4518000
M - 6 | FH - 1 - Ground Floor only |  | Family Home |  | 136 | 182 | 19000 | 2584000 |  |  |  |  | 2584000
M - 7 | FH - 5 - Ground Floor Only |  | Family Home |  | 136 | 182 | 19000 | 2584000 |  |  | 2584000
M - 8 | FH - 6 - Ground Floor Only |  | Family Home |  | 136 | 182 | 19000 | 2584000 |  |  | 2584000
M - 9 | FH - 7 & 8 -Ground Floor Only |  | Family Homes |  | 264 | 350 | 19000 | 5016000 |  |  |  | 5016000
M - 10 | Main Building - 1st Floor |  | School, Therapy & Offices |  | 1360 | 1565 | 21000 | 28560000 | [5 empty] | 28560000
M - 11 | FH - 1 - 1st Floor |  | Family Home |  | 136 | 139 | 18000 | 2448000 |  |  |  |  | 2448000
M - 12 | DG & Panel |  | Diesel Generator |  |  |  |  | 750000 |  |  | 750000
M - 13 | Central Evaporative Cooling |  | Building/ Floor-wise |  |  |  |  | 2500000 |  |  | 200000 | 200000 | 500000 | 1600000
M - 14 | Lift |  | Lift for the Main Building |  |  |  |  | 1350000 | [5 empty] | 1350000
| Total Module 0 to 14 | [6 empty] | 151573650 |  |  | 17194802.5 | 9409272.5 | 26148287.5 | 68821287.5
| Contingencies 2% | [6 empty] | 3031473 |  |  | 343896.05 | 188185.45 | 522965.75 | 1376425.75
| TOTAL | [6 empty] | 154605123 |  |  | 17538698.55 | 9597457.95 | 26671253.25 | 70197713.25
| Total Budgetary Estimate | [5 empty] | Say | 154000000 |  | 30000000 | 17500000 | 10000000 | 26500000 | 70000000
| Ashok B. Lall - Architects | [6 empty] | Rs. 15.40 Crores |  | Rs. 3 Crores | Rs. 12.40 Crores
|  |  |  | Built Area | 9534
|  |  |  | Cost/ sqm | 16152.7166
|  |  |  | Cost/ sft | 1500.624